## Sprint Backlog
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Enterprise web software development course |  | 2020-03-01 | 2020-05-01 |  | 60% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 0 |  |  | 2020-03-01 | 2020-03-14 | 13 | Complete
| Record backlog stories |  |  | 2020-03-01 | 2020-03-02 | 1 | Complete
| Database schema design |  |  | 2020-03-03 | 2020-03-07 | 4 | Complete
| Prepare for Front-end Coding |  |  | 2020-03-06 | 2020-03-09 | 3 | Complete
| Prepare for Back-end Coding |  |  | 2020-03-09 | 2020-03-13 | 4 | Complete
| Schedule Sprint Planning |  |  | 2020-03-13 | 2020-03-14 | 1 | Complete
| Sprint 1 |  |  |  |  | 0 | Complete
| Build database |  |  |  |  | 0 | Complete
| Design wireframe/mockup |  |  |  |  | 0 | Complete
| Design website interface |  |  |  |  | 0 | Complete
| Front-end coding (html,css,bootstrap) |  |  |  |  | 0 | Complete
| Design website tap and link |  |  |  |  | 0 | Complete
| Design meeting reports, dashbroards, chats and comments on website |  |  |  |  | 0 | Complete
| Implement website testing |  |  |  |  | 0 | Complete
| Sprint 2 |  |  |  |  | 0 | In Progress
| Modify database for each Back-end functions | [5 empty] | Complete
| Build Register function for unauthorized users | [5 empty] | Complete
| Implement testing Register function | [5 empty] | Complete
| Build Login/Logout function | [5 empty] | Complete
| Implement testing Login/Logout function | [5 empty] | Complete
| Build profile function (Detail, add, edit) | [5 empty] | Complete
| Implement testing for profile functions | [5 empty] | Complete
| Build reset password functions | [5 empty] | Complete
| Implement testing for password reset function | [5 empty] | Complete
| Build send and receive message function | [5 empty] | Complete
| Implement testing for send and receive message function | [5 empty] | Complete
| Build arrange and record meetings function | [5 empty] | Complete
| Implement testing for arrange and record meeting functions | [5 empty] | Complete
| Build upload documents and add comments functions | [5 empty] | Complete
| Implement testing for upload documents and add comments functions | [5 empty] | Complete
| Build blog writing function | [5 empty] | Complete
| Implement testing for blog writing function | [5 empty] | Complete
| Estalish database connection, fill data int Dashbroad and show on website interface | [5 empty] | Complete
| Implement testing for database connection, fill data int Dashbroad and show on website interface | [5 empty] | Complete
| Build allocate and deallocate functions for tutor role | [5 empty] | Complete
| Implement testing for allocate and deallocate functions | [5 empty] | Complete
| Build view the staticstics (number of messages iin the last 7 days) function for tutor role | [5 empty] | Complete
| Implement testing for the staticstics function | [5 empty] | Complete
| Build import/export functions for admin role | [5 empty] | Complete
| Implement testing for import/export functions | [5 empty] | Complete
| Build edit role function for admin role | [5 empty] | Complete
| Implement testing for edit role function | [5 empty] | Complete
| Build view a specific user's informantion function for admin | [5 empty] | Complete
| Implement testing for view a specific user's informantion function | [5 empty] | Complete
| Build change user's password function with admin's privilege | [5 empty] | Complete
| Implement testing for user's password function | [5 empty] | Complete
| Build add/disable new account functions for admin role | [5 empty] | Complete
| Implement testing for add/disable new account functions | [5 empty] | Complete
| Sprint 3 | [5 empty] | In Progress
| Sprint Planning final review | [5 empty] | Not Started
| Upload website to host server (Update and configure website settings) | [5 empty] | Not Started
| Implement final system testing | [5 empty] | Not Started
| Develop maintenance schedule for the system | [5 empty] | Not Started
| Write report documents (Group/ self evaluation) | [5 empty] | Not Started
| Write guidelines/ manuals for website | [5 empty] | Not Started
| Upload source code to githuh | [5 empty] | Not Started
| Prepare Powepoint for Presentation | [5 empty] | Not Started
| Record ScreenCast Recording | [5 empty] | Not Started