## Sprint Backlog
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Enterprise web software development course |  | 2020-03-01 | 2020-05-01 |  | 60% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 0 |  | Nguyen Quang Vinh | 2020-03-01 | 2020-03-14 | 13 | Complete
| Record backlog stories |  |  | 2020-03-01 | 2020-03-02 | 1 | Complete
| Backlog stories for Student functions |  | Nguyen Quang Vinh
| Backlog stories for Staffs functions |  | Dinh Thi Lan Hue
| Backlog stories for Staffs functions |  | Le Hong Phong
| Backlog stories for Tutor functions |  | Dao Van Hieu
| Backlog stories for Tutor functions |  | Le Thanh Trung
| Backlog stories for Admin functions |  | Lu Thua Thong
| Database schema design |  |  | 2020-03-03 | 2020-03-07 | 4 | Complete
| Schema for Blog's data flow |  | Nguyen Quang Vinh
| Schema for Comment's data flow |  | Dinh Thi Lan Hue
| Design the User's Information storaged |  | Le Hong Phong
| Design the authorities for role |  | Dao Van Hieu
| Schema for Allocation function |  | Le Thanh Trung
| Structure design for database |  | Lu Thua Thong
| Prepare for Front-end Coding |  |  | 2020-03-06 | 2020-03-09 | 3 | Complete
| Responsive website design |  | Nguyen Quang Vinh
| Sitemap |  | Dinh Thi Lan Hue
| General design for the website |  | Le Hong Phong
| Allocating design |  | Dao Van Hieu
| Design of blog page |  | Le Thanh Trung
| Design of Dashboard |  | Lu Thua Thong
| Prepare for Back-end Coding |  |  | 2020-03-09 | 2020-03-13 | 4 | Complete
| How the data being collected |  | Nguyen Quang Vinh
| Connecting the data to the web surface |  | Dinh Thi Lan Hue
| Allocating the relationship of the data |  | Le Hong Phong
| MySQL query - Field |  | Dao Van Hieu
| MySQL query - Table |  | Le Thanh Trung
| MySQL query - Relationship |  | Lu Thua Thong
| Schedule Sprint Planning |  |  | 2020-03-13 | 2020-03-14 | 1 | Complete
| Leader assign for each sprint |  | Nguyen Quang Vinh
| Recording |  | Dinh Thi Lan Hue
| Collecting member's work |  | Le Hong Phong
| Reporter |  | Dao Van Hieu
| Location booking |  | Le Thanh Trung
| Time managerment |  | Lu Thua Thong
| Sprint 1 |  |  |  |  | 0 | Complete
| Build database |  |  |  |  | 0 | Complete
| Allocating database tables |  | Nguyen Quang Vinh
| Meeting Database tables |  | Dinh Thi Lan Hue
| Message database tables |  | Le Hong Phong
| Blog database tables |  | Dao Van Hieu
| User Information database tables |  | Le Thanh Trung
| Upload File database tables |  | Lu Thua Thong
| Design wireframe/mockup |  |  |  |  | 0 | Complete
| Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page |  | Nguyen Quang Vinh
| Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages |  | Dinh Thi Lan Hue
| Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page |  | Le Hong Phong
| Edit User's Information pages, Blog management page, Blog details page, Blog Comment page |  | Dao Van Hieu
| Document comment page, Staff add user Page, Staff change information page, Message Board |  | Le Thanh Trung
| Admin change information page, Meeting management page, Uploaded file management page |  | Lu Thua Thong
| Design website interface |  |  |  |  | 0 | Complete
| Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page |  | Nguyen Quang Vinh
| Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages |  | Dinh Thi Lan Hue
| Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page |  | Le Hong Phong
| Edit User's Information pages, Blog management page, Blog details page, Blog Comment page |  | Dao Van Hieu
| Document comment page, Staff add user Page, Staff change information page, Message Board |  | Le Thanh Trung
| Admin change information page, Meeting management page, Uploaded file management page |  | Lu Thua Thong
| Front-end coding (html,css,bootstrap) |  |  |  |  | 0 | Complete
| Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page |  | Nguyen Quang Vinh
| Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages |  | Dinh Thi Lan Hue
| Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page |  | Le Hong Phong
| Edit User's Information pages, Blog management page, Blog details page, Blog Comment page |  | Dao Van Hieu
| Document comment page, Staff add user Page, Staff change information page, Message Board |  | Le Thanh Trung
| Admin change information page, Meeting management page, Uploaded file management page |  | Lu Thua Thong
| Design website tap and link |  |  |  |  | 0 | Complete
| Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page |  | Nguyen Quang Vinh
| Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages |  | Dinh Thi Lan Hue
| Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page |  | Le Hong Phong
| Edit User's Information pages, Blog management page, Blog details page, Blog Comment page |  | Dao Van Hieu
| Document comment page, Staff add user Page, Staff change information page, Message Board |  | Le Thanh Trung
| Admin change information page, Meeting management page, Uploaded file management page |  | Lu Thua Thong
| Design meeting reports, dashbroards, chats and comments on website |  |  |  |  | 0 | Complete
| Meeting report designer |  | Nguyen Quang Vinh
| Dashboard Designer for Admin |  | Dinh Thi Lan Hue
| Dashboard Designer for Tutor, Student, Staffs |  | Le Hong Phong
| Comment format design |  | Dao Van Hieu
| Chat box designer |  | Le Thanh Trung
| Chat box designer |  | Lu Thua Thong
| Implement website testing |  |  |  |  | 0 | Complete
| Tesing on Student pages |  | Nguyen Quang Vinh
| Tesing on Student pages |  | Dinh Thi Lan Hue
| Testing on Staff pages |  | Le Hong Phong
| Testing on Staff pages |  | Dao Van Hieu
| Testing on Admin Pages |  | Le Thanh Trung
| Testing on Tutor Pages |  | Lu Thua Thong
| Sprint 2 |  |  |  |  | 0 | In Progress
| Modify database design for each Back-end functions |  | Nguyen Quang Vinh, Le Hong Phong |  |  |  | Complete
| Build Register function for unauthorized users | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing Register function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build Login/Logout function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing Login/Logout function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build profile function (Detail, add, edit) | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for profile functions | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build reset password functions | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for password reset function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build send and receive message function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for send and receive message function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build arrange and record meetings function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for arrange and record meeting functions | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build upload documents and add comments functions | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for upload documents and add comments functions | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build blog writing function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for blog writing function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Estalish database connection, fill data int Dashbroad and show on website interface | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for database connection, fill data int Dashbroad and show on website interface | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build allocate and deallocate functions for tutor role | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for allocate and deallocate functions | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build view the staticstics (number of messages iin the last 7 days) function for tutor role | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for the staticstics function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build import/export functions for admin role | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for import/export functions | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build edit role function for admin role | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for edit role function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build view a specific user's informantion function for admin | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for view a specific user's informantion function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build change user's password function with admin's privilege | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for user's password function | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Build add/disable new account functions for admin role | [5 empty] | Complete
Nguyen Quang Vinh
Dinh Thi Lan Hue
Le Hong Phong
Dao Van Hieu
Le Thanh Trung
Lu Thua Thong
| Implement testing for add/disable new account functions | [5 empty] | Complete
| Tesing Plan for add/disable account |  | Nguyen Quang Vinh
| Conduct the testing on backend side |  | Dinh Thi Lan Hue
| Conduct the testing on frontend side |  | Le Hong Phong
| Sprint 3 | [5 empty] | In Progress
| Sprint Planning final review |  | Nguyen Quang Vinh |  |  |  | Not Started
| Upload website to host server (Update and configure website settings) | [5 empty] | Not Started
| Upload source |  | Dinh Thi Lan Hue
| Configure server side |  | Le Hong Phong
| Implement final system testing | [5 empty] | Not Started
| Tesing on Student pages |  | Nguyen Quang Vinh
| Tesing on General pages |  | Dinh Thi Lan Hue
| Testing on Staff pages |  | Le Hong Phong
| Testing on Comment pages |  | Dao Van Hieu
| Testing on Admin Pages |  | Le Thanh Trung
| Testing on Tutor Pages |  | Lu Thua Thong
| Develop maintenance schedule for the system |  | Le Hong Phong |  |  |  | Not Started
| Write report documents (Group/ self evaluation) | [5 empty] | Not Started
| Group Report, Individual report |  | Nguyen Quang Vinh
| Group Report, Individual report |  | Dinh Thi Lan Hue
| Group Report, Individual report |  | Le Hong Phong
| Group Report, Individual report |  | Dao Van Hieu
| Group Report, Individual report |  | Le Thanh Trung
| Group Report, Individual report |  | Lu Thua Thong
| Write guidelines/ manuals for website | [5 empty] | Not Started
| General guidelines |  | Nguyen Quang Vinh
| Manuals for using website on the basic level |  | Le Thanh Trung
| Manuals for using website on the basic level |  | Lu Thua Thong
| Upload source code to githuh | [5 empty] | Not Started
| Admin |  | Dinh Thi Lan Hue
| Admin |  | Le Hong Phong
| Prepare Powepoint for Presentation | [5 empty] | Not Started
| Presentation for all Students functions |  | Nguyen Quang Vinh
| FAQ |  | Dinh Thi Lan Hue
| FAQ |  | Le Hong Phong
| Presentation for all Admin functions |  | Dao Van Hieu
| Presentation for all Tutor functions |  | Le Thanh Trung
| Presentation for all Staff functions |  | Lu Thua Thong
| Record ScreenCast Recording |  | Lu Thua Thong |  |  |  | Not Started