## Sheet1
Question | Person | week 1 <Requirements Analysis, Schedule Planning & Initial Product Design >
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong |  | Group Meetings Schedule | Meet & Discuss with Product Owner | Organize Daily Meeting & Help with Back-end Requirements Analysis | Finalize Requirements Analysis Document | Meet with Product Owner to reconfirm Requirements
| Mr.Hieu |  | Group Meetings Schedule | Requirements Gathering | Back-end Analysis & Help with Database Design | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements
| Mr.Thong |  | Group Meetings Schedule | Requirements Gathering | Record Backlog Stories & Help with Database Design | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements
| Mr.Vinh |  | Group Meetings Schedule | Requirements Gathering | Database Design & Help with Record Backlog Stories | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements
| Mr.Trung |  | Group Meetings Schedule | Requirements Gathering | Gathering Suitable Design Environment Templates for the Project & Help with Front-end Analysis | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements
| Ms.Hue |  | Group Meetings Schedule | Requirements Gathering | Front-end Analysis & Help with Back-end Analysis | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements
What did you do today? | Mr. Phong | Group Meetings Schedule | Meet & Discuss with Product Owner | Organize Daily Meeting & Help with Back-end Requirements Analysis | Finalize Requirements Analysis Document | Meet with Product Owner to reconfirm Requirements | Allocate Works for each Team Members
| Mr.Hieu | Group Meetings Schedule | Requirements Gathering | Back-end Analysis & Help with Database Design | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements | Receive Task & Proposal Feedbacks
| Mr.Thong | Group Meetings Schedule | Requirements Gathering | Record Backlog Stories & Help with Database Design | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements | Receive Task & Proposal Feedbacks
| Mr.Vinh | Group Meetings Schedule | Requirements Gathering | Database Design & Help with Record Backlog Stories | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements | Receive Task & Proposal Feedbacks
| Mr.Trung | Group Meetings Schedule | Requirements Gathering | Gathering Suitable Design Environment Templates for the Project & Help with Front-end Analysis | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements | Receive Task & Proposal Feedbacks
| Ms.Hue | Group Meetings Schedule | Requirements Gathering | Front-end Analysis & Help with Back-end Analysis | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements | Receive Task & Proposal Feedbacks
Did you encounter any problem? | Mr. Phong | -- | -- | -- | -- | -- | --
| Mr.Hieu | -- | -- | -- | -- | -- | --
| Mr.Thong | -- | -- | -- | -- | -- | --
| Mr.Vinh | -- | -- | -- | -- | -- | --
| Mr.Trung | -- | -- | -- | -- | -- | --
| Ms.Hue | -- | -- | -- | -- | -- | --
Question | Person | week 2<Database Design>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong | Allocate Works for each Team Members | Design Room, Message & Notification Database Tables | Design Room, Message & Notification Database Tables | Design Room, Message & Notification Database Tables | Finalize Database Design | Meet with Product Owner to Discuss Overall Database Design
| Mr.Hieu | Receive Task & Proposal Feedbacks | Design Database Structure | Design Database Structure | Design Database Structure | Finalize Database Design | Meet with Product Owner to Discuss Overall Database Design
| Mr.Thong | Receive Task & Proposal Feedbacks | Design Meeting & Record Database Tables | Design Meeting & Record Database Tables | Design Meeting & Record Database Tables | Finalize Database Design | Meet with Product Owner to Discuss Overall Database Design
| Mr.Vinh | Receive Task & Proposal Feedbacks | Design Database Structure | Design Database Structure | Design Database Structure | Finalize Database Design | Meet with Product Owner to Discuss Overall Database Design
| Mr.Trung | Receive Task & Proposal Feedbacks | Design StudentID, TutorID & DashBoardInfo Database Tables | Design StudentID, TutorID & DashBoardInfo Database Tables | Design StudentID, TutorID & DashBoardInfo Database Tables | Finalize Database Design | Meet with Product Owner to Discuss Overall Database Design
| Ms.Hue | Receive Task & Proposal Feedbacks | Design User, Role & Allocation Database Tables | Design User, Role & Allocation Database Tables | Design User, Role & Allocation Database Tables | Finalize Database Design | Meet with Product Owner to Discuss Overall Database Design
What did you do today? | Mr. Phong | Design Room, Message & Notification Database Tables | Design Room, Message & Notification Database Tables | Design Room, Message & Notification Database Tables | Finalize Database Design | Meet with Product Owner to Discuss Overall Database Design | Alocating works for next week for each member
| Mr.Hieu | Design Database Structure | Design Database Structure | Design Database Structure | Finalize Database Design | Meet with Product Owner to Discuss Overall Database Design | Receive Task & Proposal Feedbacks
| Mr.Thong | Design Meeting & Record Database Tables | Design Meeting & Record Database Tables | Design Meeting & Record Database Tables | Finalize Database Design | Meet with Product Owner to Discuss Overall Database Design | Receive Task & Proposal Feedbacks
| Mr.Vinh | Design Database Structure | Design Database Structure | Design Database Structure | Finalize Database Design | Meet with Product Owner to Discuss Overall Database Design | Receive Task & Proposal Feedbacks
| Mr.Trung | Design StudentID, TutorID & DashBoardInfo Database Tables | Design StudentID, TutorID & DashBoardInfo Database Tables | Design StudentID, TutorID & DashBoardInfo Database Tables | Finalize Database Design | Meet with Product Owner to Discuss Overall Database Design | Receive Task & Proposal Feedbacks
| Ms.Hue | Design User, Role & Allocation Database Tables | Design User, Role & Allocation Database Tables | Design User, Role & Allocation Database Tables | Finalize Database Design | Meet with Product Owner to Discuss Overall Database Design | Receive Task & Proposal Feedbacks
Did you encounter any problem? | Mr. Phong | -- | -- | -- | -- | -- | --
| Mr.Hieu | -- | -- | -- | -- | -- | --
| Mr.Thong | -- | -- | -- | -- | -- | --
| Mr.Vinh | -- | -- | -- | -- | -- | --
| Mr.Trung | -- | -- | -- | -- | -- | --
| Ms.Hue | -- | -- | -- | -- | -- | --
Question | Person | week 3<Design mockup & user interface>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong | Alocating works for next week for each member | search and user interface ideas of the site | Design mockup for Home Page, Login Page and Blog Page | Design user Interface for Home Page, Login Page and Blog Page | Design user Interface for Home Page, Login Page and Blog Page | Meet the product owner to discuss and present the user interface of the site
| Mr.Hieu | Receive Task & Proposal Feedbacks | search and user interface ideas of the site | Design mockup Admin Dashboard ,Create an account Page , List account Page, Profile Page for Admin | Design user Interface Admin Dashboard ,Create an account Page , List account Page, Profile Page for Admin | Design user Interface Admin Dashboard ,Create an account Page , List account Page, Profile Page for Admin | Meet the product owner to discuss and present the user interface of the site
| Mr.Thong | Receive Task & Proposal Feedbacks | search and user interface ideas of the site | Design mockup staff Dashboard , Profile Page (staff) List student Page, List staff page | Design user Interface staff Dashboard , Profile Page (staff) List student Page, List staff page | Design user Interface staff Dashboard , Profile Page (staff) List student Page, List staff page | Meet the product owner to discuss and present the user interface of the site
| Mr.Vinh | Receive Task & Proposal Feedbacks | search and user interface ideas of the site | Add account Page (staff), Static page , Allocating page, Comments Page (Student & tutor) | Design user Interface Add account Page (staff), Static page , Allocating page, Comments Page (Student & tutor) | Design user Interface Add account Page (staff), Static page , Allocating page, Comments Page (Student & tutor) | Meet the product owner to discuss and present the user interface of the site
| Mr.Trung | Receive Task & Proposal Feedbacks | search and user interface ideas of the site | Design mockup for Student Dashboard, Upload file page (Student), Message Page (Student) Join meeting page (Student), Profile (Student) | Design user Interface for Student Dashboard, Upload file page (Student), Message Page (Student) Join meeting page (Student), Profile (Student) | Design user Interface for Student Dashboard, Upload file page (Student), Message Page (Student) Join meeting page (Student), Profile (Student) | Meet the product owner to discuss and present the user interface of the site
| Ms.Hue | Receive Task & Proposal Feedbacks | search and user interface ideas of the site | Design mockup for tutor Dashboard, Upload file page (Tutor), Message Page (Tutor) Join meeting page (Tutor), Profile (Tutor) | Design user Interface for tutor Dashboard, Upload file page (Tutor), Message Page (Tutor) Join meeting page (Tutor), Profile (Tutor) | Design user Interface for tutor Dashboard, Upload file page (Tutor), Message Page (Tutor) Join meeting page (Tutor), Profile (Tutor) | Meet the product owner to discuss and present the user interface of the site
What did you do today? | Mr. Phong | search and user interface ideas of the site | Design mockup for Home Page, Login Page and Blog Page | Design user Interface for Home Page, Login Page and Blog Page | Design user Interface for Home Page, Login Page and Blog Page | Meet the product owner to discuss and present the user interface of the site | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements
| Mr.Hieu | search and user interface ideas of the site | Design mockup Admin Dashboard ,Create an account Page , List account Page, Profile Page for Admin | Design user Interface Admin Dashboard ,Create an account Page , List account Page, Profile Page for Admin | Design user Interface Admin Dashboard ,Create an account Page , List account Page, Profile Page for Admin | Meet the product owner to discuss and present the user interface of the site | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements
| Mr.Thong | search and user interface ideas of the site | Design mockup staff Dashboard , Profile Page (staff) List student Page, List staff page | Design user Interface staff Dashboard , Profile Page (staff) List student Page, List staff page | Design user Interface staff Dashboard , Profile Page (staff) List student Page, List staff page | Meet the product owner to discuss and present the user interface of the site | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements
| Mr.Vinh | search and user interface ideas of the site | Add account Page (staff), Static page , Allocating page, Comments Page (Student & tutor) | Design user Interface Add account Page (staff), Static page , Allocating page, Comments Page (Student & tutor) | Design user Interface Add account Page (staff), Static page , Allocating page, Comments Page (Student & tutor) | Meet the product owner to discuss and present the user interface of the site | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements
| Mr.Trung | search and user interface ideas of the site | Design mockup for Student Dashboard, Upload file page (Student), Message Page (Student) Join meeting page (Student), Profile (Student) | Design user Interface for Student Dashboard, Upload file page (Student), Message Page (Student) Join meeting page (Student), Profile (Student) | Design user Interface for Student Dashboard, Upload file page (Student), Message Page (Student) Join meeting page (Student), Profile (Student) | Meet the product owner to discuss and present the user interface of the site | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements
| Ms.Hue | search and user interface ideas of the site | Design mockup for tutor Dashboard, Upload file page (Tutor), Message Page (Tutor) Join meeting page (Tutor), Profile (Tutor) | Design user Interface for tutor Dashboard, Upload file page (Tutor), Message Page (Tutor) Join meeting page (Tutor), Profile (Tutor) | Design user Interface for tutor Dashboard, Upload file page (Tutor), Message Page (Tutor) Join meeting page (Tutor), Profile (Tutor) | Meet the product owner to discuss and present the user interface of the site | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements
Did you encounter any problem? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
Question | Person | week 4<Revise the interface according to customer requirements>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements | Customize the interface according to customer requirements | Customize the interface according to customer requirements | meet customers to re-present the revised interface | 0 | 0
| Mr.Hieu | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements | Customize the interface according to customer requirements | Customize the interface according to customer requirements | meet customers to re-present the revised interface | 0 | 0
| Mr.Thong | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements | Customize the interface according to customer requirements | Customize the interface according to customer requirements | meet customers to re-present the revised interface | 0 | 0
| Mr.Vinh | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements | Customize the interface according to customer requirements | Customize the interface according to customer requirements | meet customers to re-present the revised interface | 0 | 0
| Mr.Trung | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements | Customize the interface according to customer requirements | Customize the interface according to customer requirements | meet customers to re-present the revised interface | 0 | 0
| Ms.Hue | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements | Customize the interface according to customer requirements | Customize the interface according to customer requirements | meet customers to re-present the revised interface | 0 | 0
What did you do today? | Mr. Phong | Customize the interface according to customer requirements | Customize the interface according to customer requirements | meet customers to re-present the revised interface
| Mr.Hieu | Customize the interface according to customer requirements | Customize the interface according to customer requirements | meet customers to re-present the revised interface
| Mr.Thong | Customize the interface according to customer requirements | Customize the interface according to customer requirements | meet customers to re-present the revised interface
| Mr.Vinh | Customize the interface according to customer requirements | Customize the interface according to customer requirements | meet customers to re-present the revised interface
| Mr.Trung | Customize the interface according to customer requirements | Customize the interface according to customer requirements | meet customers to re-present the revised interface
| Ms.Hue | Customize the interface according to customer requirements | Customize the interface according to customer requirements | meet customers to re-present the revised interface
Did you encounter any problem? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
Question | Person | week 5<>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
What did you do today? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
Did you encounter any problem? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
Question | Person | week 6<>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
What did you do today? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
Did you encounter any problem? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
Question | Person | week 7<>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
What did you do today? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
Did you encounter any problem? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
Question | Person | week 8< Testing & Deployment>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
What did you do today? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
Did you encounter any problem? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue