## Sheet1
Test case Author: | Nguyen Quang Vinh, Lu Thua Thong
Tester Name: | Nguyen Quang Vinh, Lu Thua Thong, Dao Van Hieu, Dinh Thi Lan Hue, Le Hong Phong, Le Thanh Trung
Project Name: | Enterprise Web Software Development
Date Tested: | 2020-04-18
Test Case ID | Test Objective ID | Category | Condition | Expected result | Actual Result | Project's Requirement
Admin's Test Log
ADLogin01 | Admin login successful with provided Username and Password | Admin Login | Username and Password must exist on the database | Redirected to the Dashboard of current admin account | Pass | Admin can login website with right Username and Password
ADLogin02 | Admin login failed with provided Username and Password | Admin Login | Username and Password did not exist on the database | Display the wrong pass/username message | Pass | Admin can login website with right Username and Password
ADDashBoard00 | Admin can view exception reports as Dashboard | Admin DashBoard | Must Login to Admin | Admin can view exception reports as Dashboard | FAIL | Admin had a dashboard
ADDashBoard00.1 | Admin can view exception reports as Dashboard | Admin DashBoard | Must Login to Admin | Admin can view exception reports as Dashboard | Pass | Admin had a dashboard
ADDashBoard01 | Admin can view exception reports | Admin DashBoard | Exception reports must have Student and Student must not have personal Tutor | Export Correct Student Information | Pass | Admin can Export Student Profile without Tutor
ADDashBoard02 | Admin cannot View exception reports | Admin DashBoard | Student that does not send or receive message for 7 to 28 days | Cannot Export Correct Student Information | Pass | Admin can Export Student Profile without Tutor
ADDashBoard03 | Admin can view total messages in 7 Days | Admin DashBoard | Display Correct Number of Messages sent in 7 Days | Correct Display of Number of Messages | Pass | Admin can Export Number of Messages for All Users
ADDashBoard04 | Admin's DashBoard will display average number of messages for All Users | Admin DashBoard | Must have at least one message in the system for display | Correct Display of Users' Fullnames and Average Messages | Pass | Admin must be able to view sisplay of Users' Fullnames and Average Messages
ADChangePassword | Admin must be able to change admin account's password | Admin Change Password | Admin must login | Admin is able to change password by entering new password details | Pass | Admin role must be able to change their current password
ADManagementRoles01 | Admin can add new role by entering new Role Name and Role Description | Admin Add New Role | Admin must click on Add New Role button | Admin is able to add new role into the system by clicking on add new role button and fill the the required fields | Pass | Admin role must be able to add new user roles
ADManagementRoles02 | Admin can edit role by entering new Role Name and Role Description | Admin Edit Role | Admin must click on Edit Role button | Admin is able to edit role in the system by clicking on edit role button and fill the the required fields | Pass | Admin role must be able to edit user roles
ADManagementRoles03 | Admin can delete role by clicking on delete button | Admin Delete Role | Admin must click on Delete Role button | Admin is able to delete role in the system by clicking on Delete Role button | Pass | Admin role must be able to delete user roles
ADManagementUsers01 | Admin can not add new user into the system | Admin Add New User | Only Admin Role can not add new users / Current Account must be Admin Account | Admin is able to add new user into the system by clicking on the Add New User button and fill in the required fields | Pass | Admin role must be able to add new user
ADManagementUsers02 | Admin can add new user into the system | Admin Add New User | Only Admin Role can add new users / Current Account must be Admin Account | Admin is able to add new user into the system by clicking on the Add New User button and fill in the required fields | FAIL | Admin role must be able to add new user
ADManagementUsers02.1 | Admin can add new user into the system | Admin Add New User | Only Admin Role can add new users / Current Account must be Admin Account | Admin is able to add new user into the system by clicking on the Add New User button and fill in the required fields | Pass | Admin role must be able to add new user
ADManagementUsers03 | Admin can edit existing users in the system | Admin Edit User | Only Admin Role can edit users / Current Account must be Admin Account | Admin is able to edit existing user in the system by clicking on the Edit User button and fill in the required fields | Pass | Admin role must be able to edit user
ADManagementUsers04 | Admin can delete existing users in the system | Admin Delete User | Only Admin Role can delete users / Current Account must be Admin Account | Admin is able to deactivate existing users by clicking on deactivate button | Pass | Admin role must be able to delete user
ADManagementTutor01 | Admin can add new tutor into the system | Admin Add New Tutor | Admin Role can add new tutors | Admin is able to add new tutor into the system by clicking on the Add New Tutor button and fill in the required fields | Pass | Admin role must be able to add new tutor
ADManagementTutor02 | Admin can edit existing tutors in the system | Admin Edit Tutor | Admin Role can edit tutors | Admin is able to edit existing tutor in the system by clicking on the Edit Tutor button and fill in the required fields | Pass | Admin role must be able to edit tutor
ADManagementTutor03 | Admin can delete existing tutors in the system | Admin Delete Tutor | Admin Role can delete tutors | Admin is able to delete tutor in the system by clicking on Delete Tutor button | Pass | Admin role must be able to delete tutor
ADManagementStudent01 | Admin can add new student into the system | Admin Add New Student | Admin Role can add new student | Admin is able to add new student into the system by clicking on the Add New Student button and fill in the required fields | Pass | Admin role must be able to add new student
ADManagementStudent02 | Admin can edit existing students in the system | Admin Edit Student | Admin Role can edit students | Admin is able to edit existing student in the system by clicking on the Edit Student button and fill in the required fields | Pass | Admin role must be able to edit student
ADManagementStudent03 | Admin can delete existing students in the system | Admin Delelete Student | Admin Role can delete students | Admin is able to delete student in the system by clicking on Delete Student button | Pass | Admin role must be able to delete student
ADManagementRoom01 | Admin can add new room into the system | Admin Add New Room | Admin Role can add new room | Admin is able to add new room into the system by clicking on the Add New Room button and fill room name | Pass | Admin role must be able to add new room
ADManagementRoom02 | Admin can edit existing rooms in the system | Admin Edit Room | Admin Role can edit rooms | Admin is able to edit existing room in the system by clicking on the Edit Room button and fill in room name | Pass | Admin role must be able to edit room
ADManagementRoom03 | Admin can delete existing rooms in the system | Admin Delete Room | Admin Role can delete rooms | Admin is able to delete room in the system by clicking on Delete Room button | Pass | Admin role must be able to delete room
ADBlog01 | Admin can create new blog | Admin Add New Blog | Admin must login | Admin successfully create a new blog post on blog page | Pass | Admin role must be able to add new blog
ADBlog02 | Admin can edit admin's blog post | Admin Edit Blog | Admin must login | Admin successfully edit blog written by admin on blog page | Pass | Admin role must be able to edit blog post written by admin
ADBlog03 | Admin can comment on all blog posts | Admin Comment Blog | Admin must login | Admin successfully comment on a blog post on blog page | Pass | Admin role must be able to comment on all blog posts
ADExport | When Admin clicks on Download button, it will automatically download User Data table | Admin Export File | Admin must login | Admin successfully export user data file by clicking on Download button | Pass | Admin role must be able to export user data file from the system
ADImport | Admin chooses correct data type file (excel) in their PC, then admin will click on Upload button to import | Admin Import File | Admin must login | Admin successfully import user data file by choose correct data type file and click on the Upload button | Pass | Admin role must be able to import user data file into the system
ADAllocate01 | Admin can allocate tutor and student to existing rooms in the system | Admin Allocate | Tutor and Student can only appear once in one room | Admin is able to allocate tutor and student to the corresponding room | Pass | Admin role must be able to allocate tutor and student to their rooms in the system
ADAllocate02 | Admin can edit tutor and student in an existing room in the system | Admin Allocate | Room must exist in the allocate management in oder for admin to perform edit function | Admin is able to edit room by adding or removing tutor and student from existing room | Pass | Admin role must be able to edit tutor and student in an existing room in the system
ADAllocate03 | Admin can delete existing room in the allocate management list | Admin Allocate | Room must exist in the allocate management in oder for admin to perform delete function | Admin is able to delete room by clicking on delete button | Pass | Admin role must be able to delete existing room in the allocate management list
ADDocument | Admin can upload new document into the system | Admin Upload Document | Admin must first choose a file to upload before clicking on upload or submit button | Admin is able upload new document into the system by choosing correct file, fill in the descriptions and click on submit button | Pass | Admin role must be able to upload new document into the system
ADMeeting01 | Admin can add new meeting in system calendar | Admin Meeting | Admin must fill in all required fields in meeting options | Admin is able to add new meeting in the system calendar | Pass | Admin role must be able to add new meeting in the system calendar
ADMeeting02 | Admin can reset meeting options to previous chosen state | Admin Meeting | The meeting fields must be already filled in order to perform reset function | Admin is able to reset meeting fields to previous choosen state by clicking on reset button | Pass | Admin role must be able to reset meeting fields
Staff's Test Log
StaffLogin01 | Staff login successfully with provided Username and Password | Staff Login | Username and Password must exist on the database | Redirected to the Dashboard of current staff account | Pass | Staff can login website with right Username and Password
StaffLogin02 | Staff login failed with provided Username and Password | Staff Login | Username and Password did not exist on the database | Display the wrong pass/username message | Pass | Staff can login website with right Username and Password
StaffDashBoard01 | Staff can view exception reports | Staff DashBoard | Exception reports must have Student and Student must not have personal Tutor | Export Correct Student Information | Pass | Staff can Export Student Profile without Tutor
StaffDashBoard02 | Staff can view exception reports | Staff DashBoard | Student that does not send or receive message for 7 to 28 days | Cannot Export Correct Student Information | Pass | Staff can Export Student Profile without Tutor
StaffDashBoard03 | Staff can view total messages in 7 Days | Staff DashBoard | Display Correct Number of Messages sent in 7 Days | Correct Display of Number of Messages | Pass | Staff can Export Number of Messages for All Users
StaffDashBoard04 | Staff's DashBoard will display average number of messages for All Users | Staff DashBoard | Must have at least one message in the system for display | Correct Display of Users' Fullnames and Average Messages | Pass | Admin must be able to view sisplay of Users' Fullnames and Average Messages
StaffChangePassword | Staff must be able to change staff account's password | Staff Change Password | Staff must login | Staff is able to change password by entering new password details | Pass | Staff role must be able to change their current password
StaffManagementRoles01 | Staff can add new role by entering new Role Name and Role Description | Staff Add New Role | Staff must click on Add New Role button | Staff is able to add new role into the system by clicking on add new role button and fill the the required fields | Pass | Staff role must be able to add new user roles
StaffManagementRoles02 | Staff can edit role by entering new Role Name and Role Description | Staff Edit Role | Staff must click on Edit Role button | Staff is able to edit role in the system by clicking on edit role button and fill the the required fields | Pass | Staff role must be able to edit user roles
StaffManagementRoles03 | Staff can delete role by clicking on delete button | Staff Delete Role | Staff must click on Delete Role button | Staff is able to delete role in the system by clicking on Delete Role button | Pass | Staff role must be able to delete user roles
StaffManagementTutor01 | Staff can add new tutor into the system | Staff Add New Tutor | Staff Role can add new tutors | Staff is able to add new tutor into the system by clicking on the Add New Tutor button and fill in the required fields | Pass | Staff role must be able to add new tutor
StaffManagementTutor02 | Staff can edit existing tutors in the system | Staff Edit Tutor | Staff Role can edit tutors | Staff is able to edit existing tutor in the system by clicking on the Edit Tutor button and fill in the required fields | Pass | Staff role must be able to edit tutor
StaffManagementTutor03 | Staff can delete existing tutors in the system | Staff Delete Tutor | Staff Role can delete tutors | Staff is able to delete tutor in the system by clicking on Delete Tutor button | Pass | Staff role must be able to delete tutor
StaffManagementStudent01 | Staff can add new student into the system | Staff Add New Student | Staff Role can add new student | Staff is able to add new student into the system by clicking on the Add New Student button and fill in the required fields | Pass | Staff role must be able to add new student
StaffManagementStudent02 | Staff can edit existing students in the system | Staff Edit Student | Staff Role can edit students | Staff is able to edit existing student in the system by clicking on the Edit Student button and fill in the required fields | Pass | Staff role must be able to edit student
StaffManagementStudent03 | Staff can delete existing students in the system | Staff Delelete Student | Staff Role can delete students | Staff is able to delete student in the system by clicking on Delete Student button | Pass | Staff role must be able to delete student
StaffManagementRoom01 | Staff can add new room into the system | Staff Add New Room | Staff Role can add new room | Staff is able to add new room into the system by clicking on the Add New Room button and fill room name | Pass | Staff role must be able to add new room
StaffManagementRoom02 | Staff can edit existing rooms in the system | Staff Edit Room | Staff Role can edit rooms | Staff is able to edit existing room in the system by clicking on the Edit Room button and fill in room name | Pass | Staff role must be able to edit room
StaffManagementRoom03 | Staff can delete existing rooms in the system | Staff Delete Room | Staff Role can delete rooms | Staff is able to delete room in the system by clicking on Delete Room button | Pass | Staff role must be able to delete room
StaffBlog01 | Staff can create new blog | Staff Add New Blog | Staff must login | Staff successfully create a new blog post on blog page | Pass | Staff role must be able to add new blog
StaffBlog02 | Staff can edit admin's blog post | Staff Edit Blog | Staff must login | Staff successfully edit blog written by admin on blog page | Pass | Staff role must be able to edit blog post written by admin
StaffBlog03 | Staff can comment on all blog posts | Staff Comment Blog | Staff must login | Staff successfully comment on a blog post on blog page | Pass | Staff role must be able to comment on all blog posts
StaffAllocate01 | Staff can allocate tutor and student to existing rooms in the system | Staff Allocate | Tutor and Student can only appear once in one room | Admin is able to allocate tutor and student to the corresponding room | Pass | Staff role must be able to allocate tutor and student to their rooms in the system
StaffAllocate02 | Staff can edit tutor and student in an existing room in the system | Staff Allocate | Room must exist in the allocate management in oder for staff to perform edit function | Staff is able to edit room by adding or removing tutor and student from existing room | Pass | Staff role must be able to edit tutor and student in an existing room in the system
StaffAllocate03 | Staff can delete existing room in the allocate management list | Staff Allocate | Room must exist in the allocate management in oder for staff to perform delete function | Staff is able to delete room by clicking on delete button | Pass | Staff role must be able to delete existing room in the allocate management list
StaffDocument | Staff can upload new document into the system | Staff Upload Document | Staff must first choose a file to upload before clicking on upload or submit button | Staff is able upload new document into the system by choosing correct file, fill in the descriptions and click on submit button | Pass | Staff role must be able to upload new document into the system
StaffMeeting01 | Staff can add new meeting in system calendar | Staff Meeting | Staff must fill in all required fields in meeting options | Staff is able to add new meeting in the system calendar | Pass | Staff role must be able to add new meeting in the system calendar
StaffMeeting02 | Staff can reset meeting options to previous chosen state | Staff Meeting | The meeting fields must be already filled in order to perform reset function | Staff is able to reset meeting fields to previous choosen state by clicking on reset button | Pass | Staff role must be able to reset meeting fields
Student's Test Log
StudLogin01 | Student login successfully with provided Username and Password | Student Login | Username and Password must exist on the database | Redirected to the Dashboard of current student account | Pass | Student can login website with right Username and Password
StudLogin02 | Student login failed with provided Username and Password | Student Login | Username and Password did not exist on the database | Display the wrong pass/username message | Pass | Student can login website with right Username and Password
StudDashBoard01 | Student can view total number of blog post | Student DashBoard | Exception reports must have Student and Student must not have personal Tutor | Export Correct Student Information | Pass | Student can Export Student Profile without Tutor
StudDashBoard02 | Student can view exception reports | Student DashBoard | Student that does not send or receive message for 7 to 28 days | Cannot Export Student Information | Pass | Student can Export Student Profile without Tutor
StudChangePassword | Student must be able to change student account's password | Student Change Password | Student must login | Student is able to change password by entering new password details | Pass | Student role must be able to change their current password
StudDocument | Student can upload new document into the system | Student Upload Document | Student must first choose a file to upload before clicking on upload or submit button | Student is able upload new document into the system by choosing correct file, fill in the descriptions and click on submit button | Pass | Student role must be able to upload new document into the system
StudMeeting01 | Student can add new meeting in system calendar | Student Meeting | Student must fill in all required fields in meeting options | Student is able to add new meeting in the system calendar | Pass | Student role must be able to add new meeting in the system calendar
StudMeeting02 | Student can reset meeting options to previous chosen state | Student Meeting | The meeting fields must be already filled in order to perform reset function | Student is able to reset meeting fields to previous choosen state by clicking on reset button | Pass | Student role must be able to reset meeting fields
StudBlog01 | Student can create new blog | Student Add New Blog | Student must login | Student successfully create a new blog post on blog page | Pass | Student role must be able to add new blog
StudBlog02 | Student can edit admin's blog post | Student Edit Blog | Student must login | Student successfully edit blog written by admin on blog page | Pass | Student role must be able to edit blog post written by admin
StudBlog03 | Student can comment on all blog posts | Student Comment Blog | Student must login | Student successfully comment on a blog post on blog page | Pass | Student role must be able to comment on all blog posts
StudChatBox | Student can chat with other users in the system | Student Chat Box | Student must login and choose another user to chat with | Student successfully send the input message and other user will see the message in their chat box | Pass | Student role must be able to chat with other user in the system
Tutor's Test Log
TurLogin01 | Tutor login successfully with provided Username and Password | Tutor Login | Username and Password must exist on the database | Redirected to the Dashboard of current student account | Pass | Tutor can login website with right Username and Password
TurLogin02 | Tutor login failed with provided Username and Password | Tutor Login | Username and Password did not exist on the database | Display the wrong pass/username message | Pass | Tutor can login website with right Username and Password
TurDashBoard01 | Tutor can view total number of blog post | Tutor DashBoard | Exception reports must have Student and Student must not have personal Tutor | Export Correct Tutor Information | Pass | Tutor can Export Student Profile without Tutor
TurDashBoard02 | Tutor can view exception reports | Tutor DashBoard | Tutor that does not send or receive message for 7 to 28 days | Cannot Export Tutor Information | Pass | Tutor can Export Tutor Profile
TurChangePassword | Tutor must be able to change student account's password | Tutor Change Password | Tutor must login | Tutor is able to change password by entering new password details | Pass | Tutor role must be able to change their current password
TurDocument | Tutor can upload new document into the system | Tutor Upload Document | Tutor must first choose a file to upload before clicking on upload or submit button | Tutor is able upload new document into the system by choosing correct file, fill in the descriptions and click on submit button | Pass | Tutor role must be able to upload new document into the system
TurMeeting01 | Tutor can add new meeting in system calendar | Tutor Meeting | Tutor must fill in all required fields in meeting options | Tutor is able to add new meeting in the system calendar | Pass | Tutor role must be able to add new meeting in the system calendar
TurMeeting02 | Tutor can reset meeting options to previous chosen state | Tutor Meeting | The meeting fields must be already filled in order to perform reset function | Tutor is able to reset meeting fields to previous choosen state by clicking on reset button | Pass | Tutor role must be able to reset meeting fields
TurBlog01 | Tutor can create new blog | Tutor Add New Blog | Tutor must login | Tutor successfully create a new blog post on blog page | Pass | Tutor role must be able to add new blog
TurBlog02 | Tutor can edit admin's blog post | Tutor Edit Blog | Tutor must login | Tutor successfully edit blog written by admin on blog page | Pass | Tutor role must be able to edit blog post written by admin
TurBlog03 | Tutor can comment on all blog posts | Tutor Comment Blog | Tutor must login | Tutor successfully comment on a blog post on blog page | Pass | Tutor role must be able to comment on all blog posts
TurChatBox | Tutor can chat with other users in the system | Tutor Chat Box | Tutor must login and choose another user to chat with | Tutor successfully send the input message and other user will see the message in their chat box | Pass | Tutor role must be able to chat with other user in the system