## Sheet1
Question | Person | week 1 <Requirements Analysis, Schedule Planning & Initial Product Design >
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong |  | Group Meetings Schedule | Backlog stories for Staffs functions | Design the User's Information storaged | Finalize Requirements Analysis Document | Meet with Product Owner to reconfirm Requirements
| Mr.Hieu |  | Group Meetings Schedule | Backlog stories for Tutor functions | Design the authorities for role | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements
| Mr.Thong |  | Group Meetings Schedule | Backlog stories for Admin functions | Structure design for database | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements
| Mr.Vinh |  | Group Meetings Schedule | Backlog stories for Student functions | Schema for Blog's data flow | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements
| Mr.Trung |  | Group Meetings Schedule | Backlog stories for Tutor functions | Schema for Allocation function | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements
| Ms.Hue |  | Group Meetings Schedule | Backlog stories for Staffs functions | Schema for Comment's data flow | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements
What did you do today? | Mr. Phong | Group Meetings Schedule | Backlog stories for Staffs functions | Design the User's Information storaged | Finalize Requirements Analysis Document | Meet with Product Owner to reconfirm Requirements | Allocate Works for each Team Members
| Mr.Hieu | Group Meetings Schedule | Backlog stories for Tutor functions | Design the authorities for role | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements | Receive Task & Proposal Feedbacks
| Mr.Thong | Group Meetings Schedule | Backlog stories for Admin functions | Structure design for database | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements | Receive Task & Proposal Feedbacks
| Mr.Vinh | Group Meetings Schedule | Backlog stories for Student functions | Schema for Blog's data flow | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements | Receive Task & Proposal Feedbacks
| Mr.Trung | Group Meetings Schedule | Backlog stories for Tutor functions | Schema for Allocation function | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements | Receive Task & Proposal Feedbacks
| Ms.Hue | Group Meetings Schedule | Backlog stories for Staffs functions | Schema for Comment's data flow | Report Analysis Findings | Meet with Product Owner to reconfirm Requirements | Receive Task & Proposal Feedbacks
Did you encounter any problem? | Mr. Phong | -- | -- | -- | -- | -- | --
| Mr.Hieu | -- | -- | -- | -- | -- | --
| Mr.Thong | -- | -- | -- | -- | -- | --
| Mr.Vinh | -- | -- | -- | -- | -- | --
| Mr.Trung | -- | -- | -- | -- | -- | --
| Ms.Hue | -- | -- | -- | -- | -- | --
Question | Person | week 2<Database Design>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong | Allocate Works for each Team Members | General design for the Database | Allocating the relationship of the data | Collecting member's work | Collecting member's work | Meet with Product Owner to Discuss Overall Design and Preperation
| Mr.Hieu | Receive Task & Proposal Feedbacks | Allocating design | MySQL query - Field | Reporter | Finalize work during week | Meet with Product Owner to Discuss Overall Design and Preperation
| Mr.Thong | Receive Task & Proposal Feedbacks | Design of Dashboard | MySQL query - Relationship | Time managerment | Finalize work during week | Meet with Product Owner to Discuss Overall Design and Preperation
| Mr.Vinh | Receive Task & Proposal Feedbacks | Responsive website design | How the data being collected | Leader assign for each sprint | Finalize work during week | Meet with Product Owner to Discuss Overall Design and Preperation
| Mr.Trung | Receive Task & Proposal Feedbacks | Design of blog page | MySQL query - Table | Location booking | Finalize work during week | Meet with Product Owner to Discuss Overall Design and Preperation
| Ms.Hue | Receive Task & Proposal Feedbacks | Sitemap | Connecting the data to the web surface | Recording | Finalize work during week | Meet with Product Owner to Discuss Overall Design and Preperation
What did you do today? | Mr. Phong | General design for the Database | Allocating the relationship of the data | Collecting member's work | Collecting member's work | Meet with Product Owner to Discuss Overall Design and Preperation | Alocating works for next week for each member
| Mr.Hieu | Allocating design | MySQL query - Field | Reporter | Finalize work during week | Meet with Product Owner to Discuss Overall Design and Preperation | Receive Task & Proposal Feedbacks
| Mr.Thong | Design of Dashboard | MySQL query - Relationship | Time managerment | Finalize work during week | Meet with Product Owner to Discuss Overall Design and Preperation | Receive Task & Proposal Feedbacks
| Mr.Vinh | Responsive website design | How the data being collected | Leader assign for each sprint | Finalize work during week | Meet with Product Owner to Discuss Overall Design and Preperation | Receive Task & Proposal Feedbacks
| Mr.Trung | Design of blog page | MySQL query - Table | Location booking | Finalize work during week | Meet with Product Owner to Discuss Overall Design and Preperation | Receive Task & Proposal Feedbacks
| Ms.Hue | Sitemap | Connecting the data to the web surface | Recording | Finalize work during week | Meet with Product Owner to Discuss Overall Design and Preperation | Receive Task & Proposal Feedbacks
Did you encounter any problem? | Mr. Phong | -- | -- | -- | -- | -- | --
| Mr.Hieu | -- | -- | -- | -- | -- | --
| Mr.Thong | -- | -- | -- | -- | -- | --
| Mr.Vinh | -- | -- | -- | -- | -- | --
| Mr.Trung | -- | -- | -- | -- | -- | --
| Ms.Hue | -- | -- | -- | -- | -- | --
Question | Person | week 3<Design mockup & user interface>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong | Alocating works for next week for each member | Message database tables | Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page | Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page | Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page | Meet the product owner to discuss and present the user interface of the site
| Mr.Hieu | Receive Task & Proposal Feedbacks | Blog database tables | Edit User's Information pages, Blog management page, Blog details page, Blog Comment page | Edit User's Information pages, Blog management page, Blog details page, Blog Comment page | Edit User's Information pages, Blog management page, Blog details page, Blog Comment page | Meet the product owner to discuss and present the user interface of the site
| Mr.Thong | Receive Task & Proposal Feedbacks | Upload File database tables | Admin change information page, Meeting management page, Uploaded file management page | Admin change information page, Meeting management page, Uploaded file management page | Admin change information page, Meeting management page, Uploaded file management page | Meet the product owner to discuss and present the user interface of the site
| Mr.Vinh | Receive Task & Proposal Feedbacks | Allocating database tables | Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page | Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page | Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page | Meet the product owner to discuss and present the user interface of the site
| Mr.Trung | Receive Task & Proposal Feedbacks | User Information database tables | Document comment page, Staff add user Page, Staff change information page, Message Board | Document comment page, Staff add user Page, Staff change information page, Message Board | Document comment page, Staff add user Page, Staff change information page, Message Board | Meet the product owner to discuss and present the user interface of the site
| Ms.Hue | Receive Task & Proposal Feedbacks | Meeting Database tables | Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages | Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages | Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages | Meet the product owner to discuss and present the user interface of the site
What did you do today? | Mr. Phong | Message database tables | Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page | Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page | Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page | Meet the product owner to discuss and present the user interface of the site | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements
| Mr.Hieu | Blog database tables | Edit User's Information pages, Blog management page, Blog details page, Blog Comment page | Edit User's Information pages, Blog management page, Blog details page, Blog Comment page | Edit User's Information pages, Blog management page, Blog details page, Blog Comment page | Meet the product owner to discuss and present the user interface of the site | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements
| Mr.Thong | Upload File database tables | Admin change information page, Meeting management page, Uploaded file management page | Admin change information page, Meeting management page, Uploaded file management page | Admin change information page, Meeting management page, Uploaded file management page | Meet the product owner to discuss and present the user interface of the site | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements
| Mr.Vinh | Allocating database tables | Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page | Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page | Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page | Meet the product owner to discuss and present the user interface of the site | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements
| Mr.Trung | User Information database tables | Document comment page, Staff add user Page, Staff change information page, Message Board | Document comment page, Staff add user Page, Staff change information page, Message Board | Document comment page, Staff add user Page, Staff change information page, Message Board | Meet the product owner to discuss and present the user interface of the site | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements
| Ms.Hue | Meeting Database tables | Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages | Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages | Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages | Meet the product owner to discuss and present the user interface of the site | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements
Did you encounter any problem? | Mr. Phong | -- | -- | -- | -- | -- | --
| Mr.Hieu | -- | -- | -- | -- | -- | --
| Mr.Thong | -- | -- | -- | -- | -- | --
| Mr.Vinh | -- | -- | -- | -- | -- | --
| Mr.Trung | -- | -- | -- | -- | -- | --
| Ms.Hue | -- | -- | -- | -- | -- | --
Question | Person | week 4<Front-end>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements | Customize the interface according to customer requirements | Coding Front-end for Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page | Dashboard Designer for Tutor, Student, Staffs | Testing on Staff pages | Write progress reports for phase 2
| Mr.Hieu | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements | Customize the interface according to customer requirements | Edit User's Information pages, Blog management page, Blog details page, Blog Comment page | Comment format design | Testing on Staff pages | Write progress reports for phase 2
| Mr.Thong | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements | Customize the interface according to customer requirements | Coding Front-end for Admin change information page, Meeting management page, Uploaded file management page | Chat box designer | Testing on Tutor Pages | Write progress reports for phase 2
| Mr.Vinh | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements | Customize the interface according to customer requirements | Coding Front-end for Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page | Meeting report designer | Tesing on Student pages | Write progress reports for phase 2
| Mr.Trung | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements | Customize the interface according to customer requirements | Coding Front-end for Document comment page, Staff add user Page, Staff change information page, Message Board | Chat box designer | Testing on Admin Pages | Write progress reports for phase 2
| Ms.Hue | organize meeting problems encountered when presenting the user interface, and plan to modify the interface according to customer requirements | Customize the interface according to customer requirements | Coding Front-end for Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages | Dashboard Designer for Admin | Tesing on Student pages | Write progress reports for phase 2
What did you do today? | Mr. Phong | Customize the interface according to customer requirements | Coding Front-end for Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page | Dashboard Designer for Tutor, Student, Staffs | Testing on Staff pages | Write progress reports for phase 2 | Organize a meeting to inform about the early stages of completion, division and planning for the back-end stage
| Mr.Hieu | Customize the interface according to customer requirements | Edit User's Information pages, Blog management page, Blog details page, Blog Comment page | Comment format design | Testing on Staff pages | Write progress reports for phase 2 | Organize a meeting to inform about the early stages of completion, division and planning for the back-end stage
| Mr.Thong | Customize the interface according to customer requirements | Coding Front-end for Admin change information page, Meeting management page, Uploaded file management page | Chat box designer | Testing on Tutor Pages | Write progress reports for phase 2 | Organize a meeting to inform about the early stages of completion, division and planning for the back-end stage
| Mr.Vinh | Customize the interface according to customer requirements | Coding Front-end for Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page | Meeting report designer | Tesing on Student pages | Write progress reports for phase 2 | Organize a meeting to inform about the early stages of completion, division and planning for the back-end stage
| Mr.Trung | Customize the interface according to customer requirements | Coding Front-end for Document comment page, Staff add user Page, Staff change information page, Message Board | Chat box designer | Testing on Admin Pages | Write progress reports for phase 2 | Organize a meeting to inform about the early stages of completion, division and planning for the back-end stage
| Ms.Hue | Customize the interface according to customer requirements | Coding Front-end for Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages | Dashboard Designer for Admin | Tesing on Student pages | Write progress reports for phase 2 | Organize a meeting to inform about the early stages of completion, division and planning for the back-end stage
Did you encounter any problem? | Mr. Phong | -- | -- | -- | -- | -- | --
| Mr.Hieu | -- | -- | -- | -- | -- | --
| Mr.Thong | -- | -- | -- | -- | -- | --
| Mr.Vinh | -- | -- | -- | -- | -- | --
| Mr.Trung | -- | -- | -- | -- | -- | --
| Ms.Hue | -- | -- | -- | -- | -- | --
Question | Person | week 5<Build general Functions>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong | Organize a meeting to inform about the early stages of completion, division and planning for the back-end stage | Modify database design for each Back-end functions | Double check the result and report | Build Add function | Double check the result and report | Build send and receive message function
| Mr.Hieu | Organize a meeting to inform about the early stages of completion, division and planning for the back-end stage | Day Off | Day Off | Build Edit function | Tesing plan for password function | Conduct the test
| Mr.Thong | Organize a meeting to inform about the early stages of completion, division and planning for the back-end stage | Implement testing Register function | Implement testing Login/Logout function | Double check the result and report | Implement testing for profile functions | Build the test plan for message function, Implement testing for password reset function
| Mr.Vinh | Organize a meeting to inform about the early stages of completion, division and planning for the back-end stage | Modify database design for each Back-end functions, Build Register function for unauthorized users | Day Off | Day Off | Build reset password functions, Conduct the test | Day Off
| Mr.Trung | Organize a meeting to inform about the early stages of completion, division and planning for the back-end stage | Day Off | Conduct the test | Build profile function (Detail, add, edit) | Conduct the test on the backend for password function | Implement testing for send and receive message function, Double check the result and report
| Ms.Hue | Organize a meeting to inform about the early stages of completion, division and planning for the back-end stage | Conduct the test | Build Login/Logout function, Build the test plan for Login/Logout function | Build View Details function | Build the testing plan for profile function | Conduct the test
What did you do today? | Mr. Phong | Modify database design for each Back-end functions | Double check the result and report | Build Add function | Double check the result and report | Build send and receive message function | Meeting with customer to confirm the final result of this week
| Mr.Hieu | Day Off | Day Off | Build Edit function | Tesing plan for password function | Conduct the test | Meeting with customer to confirm the final result of this week
| Mr.Thong | Implement testing Register function | Implement testing Login/Logout function | Double check the result and report | Implement testing for profile functions | Build the test plan for message function, Implement testing for password reset function | Meeting with customer to confirm the final result of this week
| Mr.Vinh | Modify database design for each Back-end functions, Build Register function for unauthorized users | Day Off | Day Off | Build reset password functions, Conduct the test | Day Off | Meeting with customer to confirm the final result of this week
| Mr.Trung | Day Off | Conduct the test | Build profile function (Detail, add, edit) | Conduct the test on the backend for password function | Implement testing for send and receive message function, Double check the result and report | Meeting with customer to confirm the final result of this week
| Ms.Hue | Conduct the test | Build Login/Logout function, Build the test plan for Login/Logout function | Build View Details function | Build the testing plan for profile function | Conduct the test | Meeting with customer to confirm the final result of this week
Did you encounter any problem? | Mr. Phong
Mr.Hieu
Mr.Thong
| Mr.Vinh | Database need to tobe modified fews fields characteristic
Mr.Trung
Ms.Hue
Question | Person | week 6<Build functions>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong | Meeting with customer to confirm the final result of this week | Build the test plan for blog writing function | Double check the result and report | Build blog writing function | #REF! | Build the test plan for database connection and display dashboard
| Mr.Hieu | Meeting with customer to confirm the final result of this week | Double check the result and report | Build the test plan for meeting/recording function | Implement testing for blog writing function, Conduct the test | Double check the result and report | Build allocate and deallocate functions for tutor role
| Mr.Thong | Meeting with customer to confirm the final result of this week | Build arrange and record meetings function | Build upload documents and add comments functions | Build the test plan for upload and comment function | Conduct the test | Implement testing for allocate and deallocate functions
| Mr.Vinh | Meeting with customer to confirm the final result of this week | Implement testing for arrange and record meeting functions | Implement testing for upload documents and add comments functions | Conduct the test | Implement testing for database connection, fill data into Dashboard and show on website interface, Conduct the test | Implement testing for upload documents and add comments functions
| Mr.Trung | Meeting with customer to confirm the final result of this week | Build the test plan for message function | Implement testing for upload documents and add comments functions | Implement testing for blog writing function | Implement testing for database connection, fill data into Dashboard and show on website interface | Double check the result and report
| Ms.Hue | Meeting with customer to confirm the final result of this week | conduct the test for arrange and record meeting function | Conduct the test | Double check the result and report | Establish database connection, fill data into Dashboard and show on website interface | Conduct the test
What did you do today? | Mr. Phong | Conduct the test | Double check the result and report | Build blog writing function | Build the test plan for blog writing function | Build the test plan for database connection and display dashboard | Meeting with customer to confirm the final result of this week
| Mr.Hieu | Double check the result and report | Build the test plan for meeting/recording function | Implement testing for blog writing function, Conduct the test | Double check the result and report | Build allocate and deallocate functions for tutor role | Meeting with customer to confirm the final result of this week
| Mr.Thong | Build arrange and record meetings function | Build upload documents and add comments functions | Build the test plan for upload and comment function | Conduct the test | Implement testing for allocate and deallocate functions | Meeting with customer to confirm the final result of this week
| Mr.Vinh | Implement testing for arrange and record meeting functions | Implement testing for upload documents and add comments functions | Conduct the test | Implement testing for database connection, fill data into Dashboard and show on website interface, Conduct the test | Implement testing for upload documents and add comments functions | Meeting with customer to confirm the final result of this week
| Mr.Trung | Build the test plan for message function | Implement testing for upload documents and add comments functions | Implement testing for blog writing function | Implement testing for database connection, fill data into Dashboard and show on website interface | Double check the result and report | Meeting with customer to confirm the final result of this week
| Ms.Hue | conduct the test for arrange and record meeting function | Conduct the test | Double check the result and report | Establish database connection, fill data into Dashboard and show on website interface | Conduct the test | Meeting with customer to confirm the final result of this week
Did you encounter any problem? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
Question | Person | week 7<Build functions & implementation>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong | Meeting with customer to confirm the final result of this week | Build the test plan for allocate and deallocate functions | Build import/export functions for admin role | Build edit role function for admin role | Build view user's information on staff side | Build Disable account function for admin role, Implement testing for add/disable new account functions, Report and recording the result
| Mr.Hieu | Meeting with customer to confirm the final result of this week | Build the test plan for allocate and deallocate functions | Implement testing for import/export functions | Implement testing for edit role function | Build view user's information on user side | Testing plan for password function, Conduct the testing on frontend side
| Mr.Thong | Meeting with customer to confirm the final result of this week | Build view the statistics (number of messages in the last 7 days) function for tutor role | Build the test plan for Statistics functions, Implement testing for import/export functions | Double check the final result and report | Implement testing for view a specific user's information function | Implement testing for user's password function, Conduct the test on the frontend
| Mr.Vinh | Meeting with customer to confirm the final result of this week | Conduct the test | Double check the result and report | Testing plan for edit role function | Build view a specific user's information function for admin, Implement testing for view a specific user's information function, Dashboard display testing plan | Build add/disable new account functions for admin role, Testing Plan for add/disable account
| Mr.Trung | Meeting with customer to confirm the final result of this week | Implement testing for the statistics function | Conduct the test | Build edit role function for admin role | Build view a specific user's information function for admin | Build add/disable new account functions for admin role, Conduct the test on the backend
| Ms.Hue | Meeting with customer to confirm the final result of this week | Double check the result and report | Conduct the test | Conduct the test | Build view user's information on tutor side, Conduct the test | Build change user's password function with admin's privilege, Build Add new account function for admin role, Conduct the testing on backend side
What did you do today? | Mr. Phong | Build the test plan for allocate and deallocate functions | Build import/export functions for admin role | Build edit role function for admin role | Build view user's information on staff side | Build Disable account function for admin role, Implement testing for add/disable new account functions, Report and recording the result | Meeting with customer to confirm the final result of this week
| Mr.Hieu | Build the test plan for allocate and deallocate functions | Implement testing for import/export functions | Implement testing for edit role function | Build view user's information on user side | Testing plan for password function, Conduct the testing on frontend side | Meeting with customer to confirm the final result of this week
| Mr.Thong | Build view the statistics (number of messages in the last 7 days) function for tutor role | Build the test plan for Statistics functions, Implement testing for import/export functions | Double check the final result and report | Implement testing for view a specific user's information function | Implement testing for user's password function, Conduct the test on the frontend | Meeting with customer to confirm the final result of this week
| Mr.Vinh | Conduct the test | Double check the result and report | Testing plan for edit role function | Build view a specific user's information function for admin, Implement testing for view a specific user's information function, Dashboard display testing plan | Build add/disable new account functions for admin role, Testing Plan for add/disable account | Meeting with customer to confirm the final result of this week
| Mr.Trung | Implement testing for the statistics function | Conduct the test | Build edit role function for admin role | Build view a specific user's information function for admin | Build add/disable new account functions for admin role, Conduct the test on the backend | Meeting with customer to confirm the final result of this week
| Ms.Hue | Double check the result and report | Build the test plan for import/export functions | Conduct the test | Build view user's information on tutor side, Conduct the test | Build change user's password function with admin's privilege, Build Add new account function for admin role, Conduct the testing on backend side | Meeting with customer to confirm the final result of this week
Did you encounter any problem? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue
Question | Person | week 8< Testing & Deployment>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
What did you do yesterday? | Mr. Phong | Meeting with customer to confirm the final result of this week | Testing on Staff pages | Upload website to host server (Update and configure website settings) Configure server side | Develop maintenance schedule for the system | Group Report, Individual report | Upload source code to githuh (as a admin)
| Mr.Hieu | Meeting with customer to confirm the final result of this week | Testing on Comment pages | Testing on Comment pages | Presentation for all Admin functions | Group Report, Individual report | Group Report, Individual report
| Mr.Thong | Meeting with customer to confirm the final result of this week | Testing on Tutor Pages | Record ScreenCast Recording | Write guidelines/ manuals for website Manuals for using website on the basic level | Group Report, Individual report | Group Report, Individual report
| Mr.Vinh | Meeting with customer to confirm the final result of this week | Sprint planning final review Implement final system testing Tesing on Student pages | Sprint planning final review Implement final system testing Tesing on Student pages | General guidelines | Group Report, Individual report | Presentation for all Students functions
| Mr.Trung | Meeting with customer to confirm the final result of this week | Implement final system testing Testing on Admin Pages | Implement final system testing Testing on Admin Pages | Manuals for using website on the basic level | Group Report, Individual report | Upload source code to githuh
| Ms.Hue | Meeting with customer to confirm the final result of this week | Tesing on General pages | Upload website to host server (Update and configure website settings) Upload source | Upload website to host server (Update and configure website settings) Upload source | Group Report, Individual report | Upload source code to githuh (as a admin)
What did you do today? | Mr. Phong | Testing on Staff pages | Upload website to host server (Update and configure website settings) Configure server side | Develop maintenance schedule for the system | Group Report, Individual report | Upload source code to githuh (as a admin) | FAQ
| Mr.Hieu | Testing on Comment pages | Testing on Comment pages | Presentation for all Admin functions | Group Report, Individual report | Group Report, Individual report | Presentation for all Admin functions
| Mr.Thong | Testing on Tutor Pages | Record ScreenCast Recording | Write guidelines/ manuals for website Manuals for using website on the basic level | Group Report, Individual report | Group Report, Individual report | Presentation for all Staff functions
| Mr.Vinh | Sprint planning final review Implement final system testing Tesing on Student pages | Sprint planning final review Implement final system testing Tesing on Student pages | General guidelines | Group Report, Individual report | Presentation for all Students functions | Presentation for all Students functions
| Mr.Trung | Implement final system testing Testing on Admin Pages | Implement final system testing Testing on Admin Pages | Manuals for using website on the basic level | Group Report, Individual report | Upload source code to githuh | Presentation for all Tutor functions
| Ms.Hue | Tesing on General pages | Upload website to host server (Update and configure website settings) Upload source | Upload website to host server (Update and configure website settings) Upload source | Group Report, Individual report | Upload source code to githuh (as a admin) | FAQ
Did you encounter any problem? | Mr. Phong
Mr.Hieu
Mr.Thong
Mr.Vinh
Mr.Trung
Ms.Hue