## Sprint Backlog
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | START DATE | END DATE | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Enterprise web software development course | 2020-02-29 | 2020-04-25 | 100% |  | SCOPE STATEMENT
AT RISK | TASK NAME | RESPONSIBLE | START | FINISH | STATUS | COMMENTS
| Sprint 0 |  | 2020-02-29 | 2020-03-06 | Complete
| Record backlog stories |  | 2020-02-29 | 2020-03-06 | Complete
| Backlog stories for Student functions | Nguyen Quang Vinh | 2020-02-29 | 2020-03-06 | Complete
| Backlog stories for Staffs functions | Dinh Thi Lan Hue | 2020-02-29 | 2020-03-06 | Complete
| Backlog stories for Staffs functions | Le Hong Phong | 2020-02-29 | 2020-03-06 | Complete
| Backlog stories for Tutor functions | Dao Van Hieu | 2020-02-29 | 2020-03-06 | Complete
| Backlog stories for Tutor functions | Le Thanh Trung | 2020-02-29 | 2020-03-06 | Complete
| Backlog stories for Admin functions | Lu Thua Thong | 2020-02-29 | 2020-03-06 | Complete
| Database schema design |  | 2020-02-29 | 2020-03-06 | Complete
| Schema for Blog's data flow | Nguyen Quang Vinh | 2020-02-29 | 2020-03-06 | Complete
| Schema for Comment's data flow | Dinh Thi Lan Hue | 2020-02-29 | 2020-03-06 | Complete
| Design the User's Information storaged | Le Hong Phong | 2020-02-29 | 2020-03-06 | Complete
| Design the authorities for role | Dao Van Hieu | 2020-02-29 | 2020-03-06 | Complete
| Schema for Allocation function | Le Thanh Trung | 2020-02-29 | 2020-03-06 | Complete
| Structure design for database | Lu Thua Thong | 2020-02-29 | 2020-03-06 | Complete
| Prepare for Front-end Coding |  | 2020-02-29 | 2020-03-06 | Complete
| Responsive website design | Nguyen Quang Vinh | 2020-02-29 | 2020-03-06 | Complete
| Sitemap | Dinh Thi Lan Hue | 2020-02-29 | 2020-03-06 | Complete
| General design for the website | Le Hong Phong | 2020-02-29 | 2020-03-06 | Complete
| Allocating design | Dao Van Hieu | 2020-02-29 | 2020-03-06 | Complete
| Design of blog page | Le Thanh Trung | 2020-02-29 | 2020-03-06 | Complete
| Design of Dashboard | Lu Thua Thong | 2020-02-29 | 2020-03-06 | Complete
| Prepare for Back-end Coding |  | 2020-02-29 | 2020-03-06 | Complete
| How the data being collected | Nguyen Quang Vinh | 2020-02-29 | 2020-03-06 | Complete
| Connecting the data to the web surface | Dinh Thi Lan Hue | 2020-02-29 | 2020-03-06 | Complete
| Allocating the relationship of the data | Le Hong Phong | 2020-02-29 | 2020-03-06 | Complete
| MySQL query - Field | Dao Van Hieu | 2020-02-29 | 2020-03-06 | Complete
| MySQL query - Table | Le Thanh Trung | 2020-02-29 | 2020-03-06 | Complete
| MySQL query - Relationship | Lu Thua Thong | 2020-02-29 | 2020-03-06 | Complete
| Schedule Sprint Planning |  | 2020-02-29 | 2020-03-06 | Complete
| Leader assign for each sprint | Nguyen Quang Vinh | 2020-02-29 | 2020-03-06 | Complete
| Recording | Dinh Thi Lan Hue | 2020-02-29 | 2020-03-06 | Complete
| Collecting member's work | Le Hong Phong | 2020-02-29 | 2020-03-06 | Complete
| Reporter | Dao Van Hieu | 2020-02-29 | 2020-03-06 | Complete
| Location booking | Le Thanh Trung | 2020-02-29 | 2020-03-06 | Complete
| Time managerment | Lu Thua Thong | 2020-02-29 | 2020-03-06 | Complete
| Sprint 1 |  | 2020-03-07 | 2020-04-16 | Complete
| Build database |  | 2020-03-07 | 2020-03-13 | Complete
| Allocating database tables | Nguyen Quang Vinh | 2020-03-07 | 2020-03-13 | Complete
| Meeting Database tables | Dinh Thi Lan Hue | 2020-03-07 | 2020-03-13 | Complete
| Message database tables | Le Hong Phong | 2020-03-07 | 2020-03-13 | Complete
| Blog database tables | Dao Van Hieu | 2020-03-07 | 2020-03-13 | Complete
| User Information database tables | Le Thanh Trung | 2020-03-07 | 2020-03-13 | Complete
| Upload File database tables | Lu Thua Thong | 2020-03-07 | 2020-03-13 | Complete
| Design wireframe/mockup |  | 2020-03-14 | 2020-03-20 | Complete
| Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page | Nguyen Quang Vinh | 2020-03-14 | 2020-03-20 | Complete
| Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages | Dinh Thi Lan Hue | 2020-03-14 | 2020-03-20 | Complete
| Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page | Le Hong Phong | 2020-03-14 | 2020-03-20 | Complete
| Edit User's Information pages, Blog management page, Blog details page, Blog Comment page | Dao Van Hieu | 2020-03-14 | 2020-03-20 | Complete
| Document comment page, Staff add user Page, Staff change information page, Message Board | Le Thanh Trung | 2020-03-14 | 2020-03-20 | Complete
| Admin change information page, Meeting management page, Uploaded file management page | Lu Thua Thong | 2020-03-14 | 2020-03-20 | Complete
| Design website interface |  | 2020-03-14 | 2020-03-20 | Complete
| Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page | Nguyen Quang Vinh | 2020-03-14 | 2020-03-20 | Complete
| Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages | Dinh Thi Lan Hue | 2020-03-14 | 2020-03-20 | Complete
| Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page | Le Hong Phong | 2020-03-14 | 2020-03-20 | Complete
| Edit User's Information pages, Blog management page, Blog details page, Blog Comment page | Dao Van Hieu | 2020-03-14 | 2020-03-20 | Complete
| Document comment page, Staff add user Page, Staff change information page, Message Board | Le Thanh Trung | 2020-03-14 | 2020-03-20 | Complete
| Admin change information page, Meeting management page, Uploaded file management page | Lu Thua Thong | 2020-03-14 | 2020-03-20 | Complete
| Front-end coding (html,css,bootstrap) |  | 2020-03-21 | 2020-03-27 | Complete
| Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page | Nguyen Quang Vinh | 2020-03-21 | 2020-03-27 | Complete
| Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages | Dinh Thi Lan Hue | 2020-03-21 | 2020-03-27 | Complete
| Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page | Le Hong Phong | 2020-03-21 | 2020-03-27 | Complete
| Edit User's Information pages, Blog management page, Blog details page, Blog Comment page | Dao Van Hieu | 2020-03-21 | 2020-03-27 | Complete
| Document comment page, Staff add user Page, Staff change information page, Message Board | Le Thanh Trung | 2020-03-21 | 2020-03-27 | Complete
| Admin change information page, Meeting management page, Uploaded file management page | Lu Thua Thong | 2020-03-21 | 2020-03-27 | Complete
| Design website tap and link |  | 2020-03-21 | 2020-03-27 | Complete
| Login Page, Student Dashboard, Student Join Meeting Page, Document Upload Page, Reset Password Page | Nguyen Quang Vinh | 2020-03-21 | 2020-03-27 | Complete
| Staff's User Management Page, Tutor Holding Meeting Page, Tutor Dashboard, Staff allocating pages | Dinh Thi Lan Hue | 2020-03-21 | 2020-03-27 | Complete
| Admin's User Management Page, Admin Dashboard, Admin add Role Page, Admin add user Page | Le Hong Phong | 2020-03-21 | 2020-03-27 | Complete
| Edit User's Information pages, Blog management page, Blog details page, Blog Comment page | Dao Van Hieu | 2020-03-21 | 2020-03-27 | Complete
| Document comment page, Staff add user Page, Staff change information page, Message Board | Le Thanh Trung | 2020-03-21 | 2020-03-27 | Complete
| Admin change information page, Meeting management page, Uploaded file management page | Lu Thua Thong | 2020-03-21 | 2020-03-27 | Complete
| Design meeting reports, dashbroards, chats and comments on website |  | 2020-03-21 | 2020-03-27 | Complete
| Meeting report designer | Nguyen Quang Vinh | 2020-03-21 | 2020-03-27 | Complete
| Dashboard Designer for Admin | Dinh Thi Lan Hue | 2020-03-21 | 2020-03-27 | Complete
| Dashboard Designer for Tutor, Student, Staffs | Le Hong Phong | 2020-03-21 | 2020-03-27 | Complete
| Comment format design | Dao Van Hieu | 2020-03-21 | 2020-03-27 | Complete
| Chat box designer | Le Thanh Trung | 2020-03-21 | 2020-03-27 | Complete
| Chat box designer | Lu Thua Thong | 2020-03-21 | 2020-03-27 | Complete
| Implement website testing |  | 2020-03-21 | 2020-03-27 | Complete
| Tesing on Student pages | Nguyen Quang Vinh | 2020-03-21 | 2020-03-27 | Complete
| Tesing on Student pages | Dinh Thi Lan Hue | 2020-03-21 | 2020-03-27 | Complete
| Testing on Staff pages | Le Hong Phong | 2020-03-21 | 2020-03-27 | Complete
| Testing on Staff pages | Dao Van Hieu | 2020-03-21 | 2020-03-27 | Complete
| Testing on Admin Pages | Le Thanh Trung | 2020-03-21 | 2020-03-27 | Complete
| Testing on Tutor Pages | Lu Thua Thong | 2020-03-21 | 2020-03-27 | Complete
| Sprint 2 |  | 2020-03-28 | 2020-04-17 | In Progress
| Modify database design for each Back-end functions | Nguyen Quang Vinh, Le Hong Phong | 2020-03-28 | 2020-04-03 | Complete
| Build Register function for unauthorized users | Nguyen Quang Vinh | 2020-03-28 | 2020-04-03 | Complete
| Implement testing Register function | Lu Thua Thong | 2020-03-28 | 2020-04-03 | Complete
| build the test plan for register function | Nguyen Quang Vinh | 2020-03-28 | 2020-04-03 | Complete
| conduct the test | Dinh Thi Lan Hue | 2020-03-28 | 2020-04-03 | Complete
| double check the result and report | Le Hong Phong | 2020-03-28 | 2020-04-03 | Complete
| Build Login/Logout function | Dinh Thi Lan Hue | 2020-03-28 | 2020-04-03 | Complete
| Implement testing Login/Logout function | Lu Thua Thong | 2020-03-28 | 2020-04-03 | Complete
| build the test plan for Login/Logout function | Dinh Thi Lan Hue | 2020-03-28 | 2020-04-03 | Complete
| conduct the test | Le Thanh Trung | 2020-03-28 | 2020-04-03 | Complete
| double check the result and report | Lu Thua Thong | 2020-03-28 | 2020-04-03 | Complete
| Build profile function (Detail, add, edit) | Le Thanh Trung | 2020-03-28 | 2020-04-03 | Complete
| Build View Details function | Dinh Thi Lan Hue | 2020-03-28 | 2020-04-03 | Complete
| Build Add function | Le Hong Phong | 2020-03-28 | 2020-04-03 | Complete
| Build Edit function | Dao Van Hieu | 2020-03-28 | 2020-04-03 | Complete
| Implement testing for profile functions | Lu Thua Thong | 2020-04-04 | 2020-04-10 | Complete
| conduct the test | Nguyen Quang Vinh | 2020-04-04 | 2020-04-10 | Complete
| build the testing plan for profile function | Dinh Thi Lan Hue | 2020-04-04 | 2020-04-10 | Complete
| double check the result and report | Le Hong Phong | 2020-04-04 | 2020-04-10 | Complete
| Build reset password functions | Nguyen Quang Vinh | 2020-04-04 | 2020-04-10 | Complete
| Implement testing for password reset function | Lu Thua Thong | 2020-04-04 | 2020-04-10 | Complete
| conduct the test | Dao Van Hieu | 2020-04-04 | 2020-04-10 | Complete
| double check the result and report | Le Thanh Trung | 2020-04-04 | 2020-04-10 | Complete
| build the test plan for message function | Lu Thua Thong | 2020-04-04 | 2020-04-10 | Complete
| Build send and receive message function | Le Hong Phong | 2020-04-04 | 2020-04-10 | Complete
| Implement testing for send and receive message function | Le Thanh Trung | 2020-04-04 | 2020-04-10 | Complete
| conduct the test | Le Hong Phong | 2020-04-04 | 2020-04-10 | Complete
| double check the result and report | Dao Van Hieu | 2020-04-04 | 2020-04-10 | Complete
| build the test plan for message function | Le Thanh Trung | 2020-04-04 | 2020-04-10 | Complete
| Build arrange and record meetings function | Le Thanh Trung | 2020-04-04 | 2020-04-10 | Complete
| Implement testing for arrange and record meeting functions | Le Thanh Trung | 2020-04-04 | 2020-04-10 | Complete
| conduct the test | Dinh Thi Lan Hue | 2020-04-04 | 2020-04-10 | Complete
| double check the result and report | Le Hong Phong | 2020-04-04 | 2020-04-10 | Complete
| build the test plan for meeting/recording function | Dao Van Hieu | 2020-04-04 | 2020-04-10 | Complete
| Build upload documents and add comments functions | Lu Thua Thong | 2020-04-04 | 2020-04-10 | Complete
| Implement testing for upload documents and add comments functions | Le Thanh Trung, Nguyen Quang Vinh | 2020-04-04 | 2020-04-10 | Complete
| conduct the test | Dao Van Hieu | 2020-04-04 | 2020-04-10 | Complete
| double check the result and report | Le Thanh Trung | 2020-04-04 | 2020-04-10 | Complete
| build the test plan for upload and comment function | Lu Thua Thong | 2020-04-04 | 2020-04-10 | Complete
| Build blog writing function | Le Hong Phong | 2020-04-11 | 2020-04-17 | Complete
| Implement testing for blog writing function | Lu Thua Thong, Dao Van Hieu | 2020-04-11 | 2020-04-17 | Complete
| conduct the test | Nguyen Quang Vinh | 2020-04-11 | 2020-04-17 | Complete
| double check the result and report | Dinh Thi Lan Hue | 2020-04-11 | 2020-04-17 | Complete
| build the test plan for blog writing function | Le Hong Phong | 2020-04-11 | 2020-04-17 | Complete
| Estalish database connection, fill data int Dashbroad and show on website interface | Dinh Thi Lan Hue | 2020-04-11 | 2020-04-17 | Complete
| Implement testing for database connection, fill data int Dashbroad and show on website interface | Le Thanh Trung, Nguyen Quang Vinh | 2020-04-11 | 2020-04-17 | Complete
| conduct the test | Nguyen Quang Vinh | 2020-04-11 | 2020-04-17 | Complete
| double check the result and report | Dinh Thi Lan Hue | 2020-04-11 | 2020-04-17 | Complete
| build the test plan for database connection and display dashboard | Le Hong Phong | 2020-04-11 | 2020-04-17 | Complete
| Build allocate and deallocate functions for tutor role | Dao Van Hieu | 2020-04-11 | 2020-04-17 | Complete
| Implement testing for allocate and deallocate functions | Lu Thua Thong, Dao Van Hieu | 2020-04-11 | 2020-04-17 | Complete
| conduct the test | Dinh Thi Lan Hue | 2020-04-11 | 2020-04-17 | Complete
| double check the result and report | Le Hong Phong | 2020-04-11 | 2020-04-17 | Complete
| build the test plan for allocate and deallocate functions | Dao Van Hieu | 2020-04-11 | 2020-04-17 | Complete
| Build view the staticstics (number of messages iin the last 7 days) function for tutor role | Lu Thua Thong | 2020-04-11 | 2020-04-17 | Complete
| Implement testing for the staticstics function | Le Thanh Trung | 2020-04-11 | 2020-04-17 | Complete
| conduct the test | Nguyen Quang Vinh | 2020-04-11 | 2020-04-17 | Complete
| double check the result and report | Dinh Thi Lan Hue | 2020-04-11 | 2020-04-17 | Complete
| build the test plan for Staticstics functions | Lu Thua Thong | 2020-04-11 | 2020-04-17 | Complete
| Build import/export functions for admin role | Le Hong Phong | 2020-04-11 | 2020-04-17 | Complete
| Implement testing for import/export functions | Lu Thua Thong, Dao Van Hieu | 2020-04-11 | 2020-04-17 | Complete
| build the test plan for import/export functions | Dinh Thi Lan Hue | 2020-04-11 | 2020-04-17 | Complete
| conduct the test | Le Hong Phong | 2020-04-11 | 2020-04-17 | Complete
| double check the result and report | Dao Van Hieu | 2020-04-11 | 2020-04-17 | Complete
| Build edit role function for admin role | Le Thanh Trung | 2020-04-11 | 2020-04-17 | Complete
| Implement testing for edit role function | Dao Van Hieu | 2020-04-11 | 2020-04-17 | Complete
| Testing plan for edit role function | Nguyen Quang Vinh | 2020-04-11 | 2020-04-17 | Complete
| conduct the test | Le Thanh Trung | 2020-04-11 | 2020-04-17 | Complete
| double check the final result and report | Lu Thua Thong | 2020-04-11 | 2020-04-17 | Complete
| Build view a specific user's informantion function for admin | Le Thanh Trung, Nguyen Quang Vinh | 2020-04-11 | 2020-04-17 | Complete
| Build view user's information on user side | Nguyen Quang Vinh | 2020-04-11 | 2020-04-17 | Complete
| Build view user's information on tutor side | Dinh Thi Lan Hue | 2020-04-11 | 2020-04-17 | Complete
| Build view user's information on staff side | Le Hong Phong | 2020-04-11 | 2020-04-17 | Complete
| Implement testing for view a specific user's informantion function | Lu Thua Thong, Nguyen Quang Vinh | 2020-04-11 | 2020-04-17 | Complete
| Dashboard display testing plan | Nguyen Quang Vinh | 2020-04-11 | 2020-04-17 | Complete
| conduct the test | Dinh Thi Lan Hue | 2020-04-11 | 2020-04-17 | Complete
| report and recording the result | Le Hong Phong | 2020-04-11 | 2020-04-17 | Complete
| Build change user's password function with admin's privilege | Dinh Thi Lan Hue | 2020-04-11 | 2020-04-17 | Complete
| Implement testing for user's password function | Lu Thua Thong | 2020-04-11 | 2020-04-17 | Complete
| Tesing plan for password function | Dao Van Hieu | 2020-04-11 | 2020-04-17 | Complete
| Conduct the test on the backend | Le Thanh Trung | 2020-04-11 | 2020-04-17 | Complete
| Conduct the test on the frontend | Lu Thua Thong | 2020-04-11 | 2020-04-17 | Complete
| Build add/disable new account functions for admin role | Le Thanh Trung, Nguyen Quang Vinh | 2020-04-11 | 2020-04-17 | Complete
| Build Add new account function for admin role | Dinh Thi Lan Hue | 2020-04-11 | 2020-04-17 | Complete
| Build Disable account function for admin role | Le Hong Phong | 2020-04-11 | 2020-04-17 | Complete
| Implement testing for add/disable new account functions | Le Hong Phong | 2020-04-11 | 2020-04-17 | Complete
| Tesing Plan for add/disable account | Nguyen Quang Vinh | 2020-04-11 | 2020-04-17 | Complete
| Conduct the testing on backend side | Dinh Thi Lan Hue | 2020-04-11 | 2020-04-17 | Complete
| Conduct the testing on frontend side | Le Hong Phong | 2020-04-11 | 2020-04-17 | Complete
| Sprint 3 |  | 2020-04-18 | 2020-04-25 | Complete
| Sprint Planning final review | Nguyen Quang Vinh | 2020-04-18 | 2020-04-22 | Complete
| Upload website to host server (Update and configure website settings) | Le Hong Phong, Dinh Thi Lan Hue | 2020-04-18 | 2020-04-22 | Complete
| Upload source | Dinh Thi Lan Hue | 2020-04-18 | 2020-04-22 | Complete
| Configure server side | Le Hong Phong | 2020-04-18 | 2020-04-22 | Complete
| Implement final system testing | Le Thanh Trung, Nguyen Quang Vinh | 2020-04-18 | 2020-04-22 | Complete
| Tesing on Student pages | Nguyen Quang Vinh | 2020-04-18 | 2020-04-22 | Complete
| Tesing on General pages | Dinh Thi Lan Hue | 2020-04-18 | 2020-04-22 | Complete
| Testing on Staff pages | Le Hong Phong | 2020-04-18 | 2020-04-22 | Complete
| Testing on Comment pages | Dao Van Hieu | 2020-04-18 | 2020-04-22 | Complete
| Testing on Admin Pages | Le Thanh Trung | 2020-04-18 | 2020-04-22 | Complete
| Testing on Tutor Pages | Lu Thua Thong | 2020-04-18 | 2020-04-22 | Complete
| Develop maintenance schedule for the system | Le Hong Phong | 2020-04-18 | 2020-04-22 | Complete
| Write report documents (Group/ self evaluation) |  | 2020-04-18 | 2020-04-22 | Complete
| Group Report, Individual report | Nguyen Quang Vinh | 2020-04-18 | 2020-04-22 | Complete
| Group Report, Individual report | Dinh Thi Lan Hue | 2020-04-18 | 2020-04-22 | Complete
| Group Report, Individual report | Le Hong Phong | 2020-04-18 | 2020-04-22 | Complete
| Group Report, Individual report | Dao Van Hieu | 2020-04-18 | 2020-04-22 | Complete
| Group Report, Individual report | Le Thanh Trung | 2020-04-18 | 2020-04-22 | Complete
| Group Report, Individual report | Lu Thua Thong | 2020-04-18 | 2020-04-22 | Complete
| Write guidelines/ manuals for website | Lu Thua Thong | 2020-04-23 | 2020-04-24 | Complete
| General guidelines | Nguyen Quang Vinh | 2020-04-23 | 2020-04-24 | Complete
| Manuals for using website on the basic level | Le Thanh Trung | 2020-04-23 | 2020-04-24 | Complete
| Manuals for using website on the basic level | Lu Thua Thong | 2020-04-23 | 2020-04-24 | Complete
| Upload source code to githuh | Le Thanh Trung | 2020-04-23 | 2020-04-24 | Complete
| Admin | Dinh Thi Lan Hue | 2020-04-23 | 2020-04-24 | Complete
| Admin | Le Hong Phong | 2020-04-23 | 2020-04-24 | Complete
| Prepare Powepoint for Presentation |  | 2020-04-23 | 2020-04-24 | Complete
| Presentation for all Students functions | Nguyen Quang Vinh | 2020-04-24 | 2020-04-25 | Complete
| FAQ | Dinh Thi Lan Hue | 2020-04-24 | 2020-04-25 | Complete
| FAQ | Le Hong Phong | 2020-04-24 | 2020-04-25 | Complete
| Presentation for all Admin functions | Dao Van Hieu | 2020-04-24 | 2020-04-25 | Complete
| Presentation for all Tutor functions | Le Thanh Trung | 2020-04-24 | 2020-04-25 | Complete
| Presentation for all Staff functions | Lu Thua Thong | 2020-04-24 | 2020-04-25 | Complete
| Record ScreenCast Recording | Lu Thua Thong | 2020-04-24 | 2020-04-25 | Complete