## Current Iteration
|  | Iteration Number: |  |  |  | 1
|  | Expected Total effort: |  |  |  | 55
|  | Days In Sprint: |  |  |  | 40
Burndown Chart
User Stories |  | Days (Points Completed) | [39 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | Task Balance | Percentage Completed
As an unahotirzed user, I want to be able to create a new account | 2 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 1 to Days (Points Completed) 2
As an unauthorized user, I want to be able to login to the system | 1 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 3
As an unauthorized user, I want to be able to logout of the system | 1 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 4
As an authorized user, I want to be able to view my profile | 1 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 5
As an authorized user, I want to be able to edit my profile | 2 | [40 empty] | -1 | 150% | bar: Days (Points Completed) 4 to Days (Points Completed) 6
As an authorized user, I want to be able to reset my password in case I forgot it | 1 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 6
As an authorized user, I want to be able send and receive message from other system users/roles | 5 | [40 empty] | -2 | 140% | bar: Days (Points Completed) 5 to Days (Points Completed) 11
As an authorized user, I want to arrange and record meetings including time, place, type, topics and take notes | 5 | [40 empty] | 3 | 40% | bar: Days (Points Completed) 9 to Days (Points Completed) 10
As an authorized user, I want to upload documents and make my own comments on them | 4 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 10 to Days (Points Completed) 13
As an authorized user, I want to be able to write my own blog | 5 | [40 empty] | -1 | 120% | bar: Days (Points Completed) 13 to Days (Points Completed) 18
As an authorized user, I want to be able to view my own DashBoard where I can find the summarization about my interactions with other users/roles | 3 | [40 empty] | 1 | 66.67% | bar: Days (Points Completed) 18 to Days (Points Completed) 19
As a Tutor, I want to be able to allocate and deallocate students/tutors | 6 | [40 empty] | -1 | 116.7% | bar: Days (Points Completed) 17 to Days (Points Completed) 23
As a Tutor, I want to be able to view DashBoard of students/tutors | 2 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 23 to Days (Points Completed) 24
As a Tutor, I want to be able to view the Statistics (number of messages in the last 7 days) | 3 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 25 to Days (Points Completed) 27
As a system Admin, I want to import/export user data from MIS system or at least import/export from file | 3 | [40 empty] | 1 | 66.67% | bar: Days (Points Completed) 28 to Days (Points Completed) 29
As a system Admin, I want to view all users and their roles in the system | 2 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 30 to Days (Points Completed) 31
As a system Admin, I want to view a specific user's information | 2 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 32 to Days (Points Completed) 33
As a system Admin, I want to be able to change user's role | 2 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 34 to Days (Points Completed) 35
As a system Admin, I want to be able to change user's password in case they cannot | 2 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 36 to Days (Points Completed) 37
As a system Admin, I want to be able to remove or add new user into the system | 3 | [40 empty] | 0 | 100% | bar: Days (Points Completed) 38 to Days (Points Completed) 40
Effort Remaining | 55 | 54 | 53 | 52 | 50 | 47 | 44 | 43 | 42 | 40 | 37 | 35 | 34 | 32 | 31 | 30 | 29 | 27 | 24 | 22 | 21 | 20 | 19 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 100%
Ideal Trend | 55 | 53.625 | 52.25 | 50.875 | 49.5 | 48.125 | 46.75 | 45.375 | 44 | 42.625 | 41.25 | 39.875 | 38.5 | 37.125 | 35.75 | 34.375 | 33 | 31.625 | 30.25 | 28.875 | 27.5 | 26.125 | 24.75 | 23.375 | 22 | 20.625 | 19.25 | 17.875 | 16.5 | 15.125 | 13.75 | 12.375 | 11 | 9.625 | 8.25 | 6.875 | 5.5 | 4.125 | 2.75 | 1.375 | 0
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days